## Project Plan
PROJECT X - AUTOMATED ATTENDANCE SYSTEM
Start date - March 1, 2025 |  |  | End date - May 2, 2025 |  |  | Actual end date - In Progress
Task ID | Task Name | Sub Task ID | Sub Task Name | Deliverables | Estimated Days | Start Date | End Date | Days Used | Status | Assignee
1 | Project Initiation | 1.1 | Define project objectives | Project scope document | 1 | 2025-03-20 | 2025-03-20 | 1 | Done
|  | 1.2 | Identify stakeholders | Stakeholder list | 1 | 2025-03-21 | 2025-03-21 | 1 | Done
|  | 1.3 | Conduct feasibility study | Feasibility report | 1 | 2025-03-22 | 2025-03-22 | 1 | Done
|  | 1.4 | Create project plan | Project plan document | 1 | 2025-03-23 | 2025-03-23 | 1 | Done
|  | 1.5 | Obtain approvals | Approved project charter | 1 | 2025-03-24 | 2025-03-24 | 1 | Done
2 | Requirement Analysis | 2.1 | Gather functional requirements | Requirement specification document | 1 | 2025-03-25 | 2025-03-25 | 1 | Done
|  | 2.2 | Gather non-functional requirements | Performance & security requirements | 1 | 2025-03-26 | 2025-03-26 | 1 | Done
|  | 2.3 | Define system architecture | System architecture diagram | 2 | 2025-03-27 | 2025-03-28 |  | Pending
|  | 2.4 | Create wireframes/mockups | UI wireframes | 2 | 2025-03-29 | 2025-03-30 |  | Pending
3 | Design Phase | 3.1 | Database design | ERD and database schema | 3 | 2025-03-31 | 2025-04-02 |  | Pending
|  | 3.2 | API design | API documentation | 2 | 2025-04-03 | 2025-04-04 |  | Pending
|  | 3.3 | UI/UX design | Final UI/UX designs | 2 | 2025-04-05 | 2025-04-06 |  | Pending
|  | 3.4 | Security design | Security measures document | 4 | 2025-04-07 | 2025-04-10 |  | Pending
4 | Development Phase | 4.1 | Set up development environment | Configured development tools | 1 | 2025-04-11 | 2025-04-11 |  | Pending
|  | 4.2 | Frontend development (React Native) | Initial UI screens | 3 | 2025-04-12 | 2025-04-14 |  | Pending
|  | 4.3 | Backend development | Working backend APIs | 5 | 2025-04-15 | 2025-04-19 |  | Pending
|  | 4.4 | QR Code scanning implementation | Functional QR scanner module | 2 | 2025-04-20 | 2025-04-21 |  | Pending
|  | 4.5 | GPS validation implementation | Functional GPS validation | 3 | 2025-04-22 | 2025-04-24 |  | Pending
|  | 4.6 | Secure storage implementation | Encrypted storage module | 2 | 2025-04-25 | 2025-04-26 |  | Pending
|  | 4.7 | Testing unit integration | Test reports | 1 | 2025-04-27 | 2025-04-27 |  | Pending
5 | Testing & QA | 5.1 | Functional testing | Test case reports | 1 | 2025-04-28 | 2025-04-28 |  | Pending
|  | 5.2 | Security testing | Security vulnerability report | 1 | 2025-04-29 | 2025-04-29 |  | Pending
|  | 5.3 | User acceptance testing | User feedback & approval | 1 | 2025-04-30 | 2025-04-30 |  | Pending
6 | Deployment | 6.1 | Prepare deployment environment | Deployment guide | 1 | 2025-05-01 | 2025-05-01 |  | Pending
|  | 6.2 | Deploy backend API | Hosted backend | 2 | 2025-05-02 | 2025-05-03 |  | Pending
|  | 6.3 | Deploy mobile app (beta) | Beta version released | 1 | 2025-05-04 | 2025-05-04 |  | Pending
|  | 6.4 | Fix deployment issues | Issue resolution report | 3 | 2025-05-05 | 2025-05-07 |  | Pending
|  | 6.5 | Release final version | Live mobile app | 1 | 2025-05-08 | 2025-05-08 |  | Pending
7 | Final Demonstration | 7.1 | Prepare presentation materials | Presentation slides | 1 | 2025-05-09 | 2025-05-09 |  | Pending
|  | 7.2 | Conduct demo for stakeholders | Live demonstration | 1 | 2025-05-10 | 2025-05-10 |  | Pending
|  | 7.3 | Gather final feedback | Feedback report | 1 | 2025-05-11 | 2025-05-11 |  | Pending
|  | 7.4 | Project closure & documentation | Final project report | 1 | 2025-05-12 | 2025-05-12 |  | Pending
Formulas:
End Date = IF([Days Used]<>"", [Actual end date - In Progress] + [Days Used] - 1, [Actual end date - In Progress] + [Estimated Days] - 1)
Actual end date - In Progress = [End Date, row above] + 1